## ISSUES
Issue # | Priority | Reference # | Subject | Area | Description | 2016-02-16 | User | Status | Resolution | Notes
73 | A | RFE-155 | Archer Stage url should be included in ASM description/comments |  | i.e. autopopulate the comments/description field in the assessment request pop-up with the Stage URL | 2015-03-24 | Web Ops | OPEN | TBD
74 | A | RFE-156 | A field should be added to websites view archer panel to show the state of the records stage url |  |  | 2015-03-24 | Web Ops | OPEN | TBD
75 | A | RFE-157 | Gitlab panel ssh url link redirects to invalid address if clicked while ssh url is already displayed |  |  | 2015-03-24 | INetU/Prime | OPEN | Scheduled for 2.5 | 3/28/16 - to be in next release (2.5)
76 | A | RFE-158 | DeSMan should periodically check for updates from Archer API for all open assessments |  | Currently, users must visit the page for the refresh to happen… will change to cron job that periodically updates info in DB… allows users to accept merge requests faster, and allows for reporting on data | 2015-03-24 | INetU/Prime | OPEN | Scheduled for 2.5 | 3/28/16 - to be in next release (2.5)
77 | A | RFE-159 | As an administrator, you should be able to access ALL of the records in DeSMan UI |  |  | 2015-03-24 | INetU/Prime | OPEN | Scheduled for 2.5 | 3/28/16 - to be in next release (2.5)
78 | A | RFE-160 | DeSMan sometimes triggers multiple requests to Archer for assessments |  |  | 2015-03-24 | INetU/Prime | OPEN | Scheduled for 2.5 | 3/28/16 - to be in next release (2.5)
79 | A |  | Refactoring Prepare DB functioanlity | Prepare DB Functionality | Improvements to functionality focused on issue of container losing track of jobs it's working on/focus on buckets, etc NOTE: more incremental improvement than #46 which is to test/use a WP plugin to supplement this | 2016-03-28 | INetU/Prime | OPEN
46 | B | SONY-517014 | Preview URL pointing to stage not devel | Prepare DB Functionality | antoniolizana.net We generated a preview of the devel site so we could share the link with the product manager who was outside Sony's office and we found out that the images were not loading correctly. It seems to be a problem in the URL pointing to "stage" instead of pointing to "devel". (see email 12/24/2015 8:54) | 2015-12-21 | Alberto Gonzalez - Spain | OPEN | INetU Investigating | 01/06/16 - John to re-create issue in lab to trouble-shoot 1/14/16 - JF involves automatic re-write of DB which could be prone to errors-(invalid paths); Can we migrate this feature to a WP plug-in instead of Desman (Search/replace DB 2?)--- Bill to set up call w/ Haydur & John, Chris, Kevin 1/20/16 - need to get the Prepare DB feature into a Wordpress plugin- Bill to set up meeting with Haydur 1/27/16 - Met with Haydur; he's ok with it but wants to test the plug-in: Velvet Blues Update URLS; make it available to all new Wordpress sites, and users can activate it when needed... John to add it to the infosec test site for testing 2/10/16 - John to coordinate with Haydur to add this to a test Desman site so Haydur can review the plug-in (Velvet Blues) 3/2/16 - Prepare DB issue occurred with Ray@45Press (SONYDFA-526570)
61 | B |  | Allow users to click "Re-Try" button for Desman Errors | Error Management | When a process fails in Desman, the error log shows a list of processes that, if you have the right security access, will allow you to click a "Re-try" button to try to re-run the process and get past the error This request is to give the typical label power-user the ability to re-run errored-out processes so that they can potentially move past these errors without INetU intervention | 2015-11-25 | Neato - UK | OPEN |  | 1/29/16 - JF - currently working fix to allow all processes to be re-run smoothly, then we can open this feature up to users 2/10/16 - John to fix existing re-try issue before we give users access to this… but prioritize as B for now since there are not too many retrys needed 3/2/16 - if we do roll out need to train users not to restart processes over and over 3/16/16 - we've enhanced logic around restart functionality, so this may be safer to give to users; but will still need training for users ---should we wait until we have local user profile setup functionality before deploying this so we can narrow this re-try capability to very specific experienced users?
62 | B |  | Clear Cache Functionality | CloudFlare Clear Cache Functionality | KL -James @ 45Pres had ping’d me asking to clear cache for a website he was updating. He also suggested this would be a nice feature to add to Desman ( Bill – can you add that to the enhancement list? I think there are CloudFlare api’s that might be available to us to allow this). | 2016-01-11 | James - 45Press | OPEN |  | 1/22/16 - KL - Bill F/John F – noting again that it would be nice to have this in Desman; and perhaps in Desman (with a more complex site), it would be nice to offer the ability to purge only the changed files 1/29/16 - INetU currently looking at a few solutions for purging cache at cloudflare (Wordpress vs. deployment events) 2/10/16 - INetU to work with Prime on implementing this... as a first pass, we should plan to purge everything (as in FastTrack)... will get feedback from developers on best approach 3/2/16 - Cloudflare does not cache a lot for dynamic sites...more for static...so not as urgent; mostly images, etc; W3 Total Cache takes care of the rest 3/16/16 - Need to have analysis meeting to determine best way to implement this; could we employ W3 Total Cache to interfae with CloudFlare for wordpress sites
67 | B | RFE-144 | Make Preview URLs more intuitive |  | Currently preview URLS include site ID; could the preview include Artist name/site name so user can more easily remember the links | 2016-01-29 | Conference (Jamie-Nashville) | OPEN |  | 2/10/16 - this pertains to all URLs --all use website ID and district… not as friendly, but def interested in improving; fairly complex enhancement (impacts a lot of system componenets) 3/2/16 - change involves coordinated update to multiple systems and existing site update/cleanup
60 | C |  | Automate adding "www" to alias if user does not already include it | Production - Subdomain Creation | Automatically add "www" version of URL as an alias if the user does not originally include "www" when keying in the Domain field upon creating the site If user does not add "www", then prompt user to add or not | 2015-11-19 | Daniel - Germany | OPEN |  | 11/19/15 - Original Issue: jarre-electronica.com Daniel: we configured the domain equal to jarre-electronica.com but only the non-www domain is working properly. Unfortunate the www domain runs into a CF 504. Is this a config issue or an INetU host issue? Tony: Hi Daniel / Tommy – For die-firma-singt.de, it looks like you will need to add an alias for the www subdomain. Please remember that alias changes in DeSMan require a deployment in order for the changes to take effect. For jarre-electronica.com, both the root and www subdomain is working properly; I performed a CURL on both URLs and receiving properly responses. Can you check this one again? Daniel: misunderstanding, jarre-electronica.com works properly. I just wanted to point out, that our DNS config is the same for die-firma-singt.de. As far as I know, we didn’t need to create the www subdomain for DeSMan sites in the past. Isn’t that some thing that needs to automated? For my understanding a www subdomain is need in most cases. 11/19/15 - site deployed under one name, but deployed under different aliases; i.e. jarre-electronica.com vs. www.jarre-electronica.com; Should Desman automatically pre-pend the domain with "www"...i.e. if user did not already have it in there (probably would work for most cases) Current Logic : If you include the www in the URL on site creation, when deployed to PROD, the system will automatically include the www as well as the root domain. If you only put in the root domain, the system currently will not automatically add the www subdomain. So if you want aliases to be automatically created for both the www and root, please make sure to include the “www” subdomain when you add a site record for DeSMan. RFE Request: include the www subdomain (if the user did not already include it) to the alias list. Since there is a workaround as detailed above, this will be a lower priority request. 2/10/16 - Since we rolled alias change in which they are updated immediately (instead of upon next deploy), what is the priority now?
27 | C | #SONY-509000 RFE# 125 | Object Storage Problem | Production - Object Storage Problem | auth3... .de Add Object Storage does not work For example: https://desman.smehost.net/websites/view/200 and https://desman.smehost.net/websites/view/222 | 2015-11-24 | Anton - Germany | OPEN | RFE created | 11/24/15 - Pending INetU review 12/1/15 - decided they needed S3 after they already created Devel and promoted to Stage; when tried to create S3 after having created Stage, won't work... INetU needs to create manually... Limitation of system... Need to enhance so we can add an object store even after Stage was created--to create RFE 12/2/15 - Requesting object-storage should create buckets for all deployed instances of site #125 12/8/15 - To be addressed after a handful of existing bug fixes are done (i.e. tied to Archer URL issue, etc) 12/9/15 - Ray/James did not experience this issue 12/23/15 - Targeting first week in Jan for release 01/6/16 - Still in progress 01/14/16 - To be released with all OBS enhancements... 1-2 weeks... update next week 01/20/16 - John to start it soon 3/2/16 - We can pick this back up when resources free up
52 | C | #SONYDFA-520338]: us-rca / avrillavigne.com creation #SONYDFA-519535]: ca / celinedion.com creation #SONYDFA-520542]: us-epic / epicrecords.com db import stuck? #SONYDFA-520583]: us-rca / pinkspage.com devel promotion stuck? SONYDFA-520585]: us-legacy / paulsimon.com database promotion stuck? | Desman Performance/Delays |  | avrillavigne.com Deployment status icons all looked completed, but no green button available; there was a message in its place (did not get a screenshot of this in time before InetU fixed site) celinedion.com Devel environment DB process stuck running… devel button is orange, Stage is green…unclear what is going on - see screenshot epicrecords.com Seems to have taken 25 minutes for a DB import done on this site (after Devel environment was completed successfully) pinkspage.com Devel to Stage promotion stuck… Mike Lily had to manually promote the OBS and database to stage paulsimon.com Devel to Stage promotion stuck… Mike Lily had to manually promote the OBS and database to stage | 2016-01-22 | Multiple | OPEN | Analysis Pending | 1/22/16 - (busier day) Unusually large amount of deployments causing others to be delayed (queued); could be related to multiple deployments on raleighritchie.com site that were done one after another --but this seemed to complete the tasks and just showed a blue error message area where the button normally appears 1/22/16 - Celinedion.com - identified an image file with a cryptic name--the process got stuck on this file 1/27/16 - Multiple Causes: -Openshift/Broker issues--once we get rid of all Openshift sites, we can remove functionality -Support re-started jobs inadvertently...which added to delays, but this can be avoided in future -A lot more sites being worked on this day (i.e. Ray had to push 5 sites into scan) -Users submitting multiple deployments concurrently (maybe more than necessary) - i.e. within avrillavigne.com... within 10 minutes, there were 10 push requests (frequent commits are fine, but many pushes consecutively can be problematic)... users need to look at each push's status in the Deployment Status page before pushing more code via GIT - John to pull history of these deployments to see how fast/slow each were running, when they were run, etc. -5 deployments pushed close together for ralieghritchie.com 2/10/16 - John to pull together history
63 | C |  | WordPress Plugin Updates |  | Launch Plugin Updates from Desman front-end; Allow use to choose which plugins to update; notify users when plugins are out of date | 2016-01-26 | Web Ops | OPEN |  | 1/29/16 - JF, DS - perhaps a dashboard like page which lists all avaiable plugins, indicates which ones are out of date, and allows users to select one or many plugins to be updated; access to this functionality could be located at bottom of site maintenance page along with other WordPress information 2/10/16- fairly complex enhancement; will be useful but priority not urgent
66 | C | RFE-145 | Allow users to mark a site for decommissioning |  | Within the app, user can flag the site for decommissioning and this would notify INetU | 2016-01-29 | Conference | OPEN |  | 2/10/16 - first this stab could be just a flag, but later we could determine what if any fucntionality can be tied to it (if needed)
Note on I1: OPEN -reported and clarification and specification not finalized READY FOR DEV READY TO TEST ON HOLD -it is not worked on CLOSED -successfully tested REMOVED -not applicable/nothing will be done for it

## ON HOLD
Issue # | Reference # | Subject | Area | Description | Date | User | Status | Resolution | Notes
2 | SONYDFA-506119 SONYDFA-502645 | Sites awaiting security assessment could be impacted by interim Word Press updates | Production - Word Press update & sites pending security assessment | When user promoted syntechofficial.com to prod Desman created all of the backend structures (DB, Docker container, S3 object store, Git etc) and a security assessment was created The assessment took more than 2 weeks to complete. In the interim INetU, pushed updates to Word Press/GitLab. When security assessment completed, users attempted to promote to Prod again, but the process failed, requiring manual intervention from INetU Failure due to site's Git version being out of sync with updates made (i.e. site in a security assessment state were excluded from the Gitlab update and therefore became out of sync) | 2015-11-10 | Ray - 45Press | ON HOLD | Unable to Reproduce | 11/19/15 - Wordpress update was pushed by INETU to update all out-of-date sites; David Six- script can be programed to avoid updating sites that have pending processes--currently identifies if changes exist between dev/stage/prod and avoids. Can we check the site status(s) within the script? This is a Wordpress update script issue: next time Wordpress update script is run, identify any sites incorrectly updated; determine how to improve script to avoid sites with these attributes.
5 | SONY-506299 | Stage Promotion Button Disappeared on ineterface | Production - Promoting To Stage | When Neato promoted adysuleimanofficial.com to stage for the 2nd time, the button disappeared; INetU manually intervened to allow him to continue | 2015-11-12 | Neato - UK | ON HOLD | Unable to Reproduce | 11/19/15 - this issue happened 1 time; unable to reproduce the button disappearing...need to identify when this happens again and determine how to reproduce; by walking through the steps with the user
6 | N/A | Desman 2.1 Demo - Container Creation did not resolve | Desman 2.1 - Container Creation | During Desmon 2.1 demo, progress indicator icon for creation of a container (when building Stage environment) kept running/did not resolve... could be related to an issue with export of S3 bucket contents from Devel to Stage (John looking into it) | 2015-11-10 | John Fanjoy |  | Desman 2.1
7 | N/A | Desman 2.1 Demo - Cron Job error | Desman 2.1 - Cron Job Module | Cron Job creation had an issue when creating new job (John looking into it) | 2015-11-10 | John Fanjoy |  | Desman 2.1
8 | N/A | Desman 2.1 Demo - Show Current Deployments buttons automatically | Desman 2.1 - Deployment Status Indicators function | When all of the processes are completed for a given deployment (i.e. all icons change to ones with green checks), can we have the environment button (i.e. the green “Devel”, “Stage” or “Prod” buttons) automatically appear (instead of the user having to manually refresh the page) | 2015-11-10 | Tony Shin |  | Desman 2.1
18 | SONYDFA-507850 | Deploy to Stage - no URL | Production - Deploying to Stage | jimihendrix.com stage url missing; Promoted this to stage and the URL did not pop up in desman. Can I also have OBS promoted as well so we can get this into scan today? | 2015-11-18 | Ray - 45Press | ON HOLD | Unable to Reproduce | 11/19/15 - looks like change was pushed to stage branch before the create job completed... We display the Promote button immediately (when Devel button appears); 11/24/15 - when site redeployed manually, issue resolved, but no log error to look at...need to reproduce problem
22 | SONYDFA-508282 | Archer API Communications failure | Production - prod deployment failed due to failed API call | outkast.com Need OBS promoted to prod, also seeing this error in Desman: > One or more deployments has failed. - /websites/Please contact an administrator to continue The OBS content has been promoted and images have been fixed. In the deployments history the error that showed for "One or more deployments has failed. - /websites/Please contact an administrator to continue" was that "An Exception occurred while trying to save a new Archer assessment" This is an external HTTP API that could fail to respond. That Error is the response. You can clear the error or view what is going on by clicking on the gear and selecting "Review Errors" highlighted in red or the "Deployment History" selection. The error will show in red in those logs and you can click to acknowledge them. The Prod URL is as follows: | 2015-11-20 | Ray - 45Press | ON HOLD | Determine Frequency/Reproduce | 11/24/15 - This is an external HTTP API that could fail to respond... Archer API communications issue If this becomes a habitual problem, we may need to create functiaonlity that identifies the error has occurred, and allows the user to re-try issuing the assessment (currently, only an Admin user can re-issue the assessment after a fail like this); alternately, we could program the system to automatically re-try issuing the assessment
32 | N/A | Word Press Admin very slow | Word Press Admin | James indicated that the WordPress Admin performance is very slow; i.e. moving from page to page takes a lot longer for most Desman sites than non-Desman | 2015-12-01 | James - 45Press | ON HOLD | Needs Analysis | 12/1/15 - may be some resource tweaking that can be done from container perspective to improve performance; we should define the performance benchmark for the Admin side that's appropriate... Let's reproduce the performance issue (i.e. is it .5 seconds, 1 second, 2 second?) 12/8/15 - To be investigated at after other priority issues 12/9/15 - Ray/James ...slow downs happening upon creating new page, creating new post, navigating, saving settings pages... can take 10-30 seconds longer than expected 12/15/15 - Ray/James to come up with common scenario in Wordpress Admin (very common task which takes some time) 12/23/15 - No feedback from Ray/James - Bill to follow upw 01/06/16 - Followed up with Ray/James - have not provided any scenarios to test yet 01/16/16 - to put on hold until users make this a priority--no feedback from 45Press
34 | #SONY-510527 | Site Error Status Showing |  | docs.sonymusic.de It appears that this is a reporting issue - from what I can see the site is set up properly but shows an error status. I will ask John to take a look at why you are getting errors. If possible I would like to delay clearing the error on pastewka.slotmachine.sme-apps.com so that he has an example to work with. If you need to work on this site immediately and would like to use a different error as an example let me know. -David Six | 2015-12-03 | Daniel - Germany | ON HOLD | Micro Release 2.1.2 | 12/8/15 - Upon site creation, had issues with cloning Git Repo which prevented web hooks from being added... when manually added web hooks, added to wrong group (DE-labels but needed to be under DE-Internal); we think this Repo cloning issue has been resolved with 2.1.2, but we can keep an eye open for this issue in future Additional bug fix being worked on to improve logging for issues similar to this 12/9/15 - Ray/James did not experience this issue
36 | #SONYDFA-511507 RFE #131 | Devel to Stage deployment/S3 deploy still spinning | Deploying Devel to Stage | r-kelly.com Problem attributed to clicking Request Latest Merge Request button too soon after having pushed Stage to Prod; However, the S3 icon in Stage is still spinning... Could that have something to do with the original problem? James says he doesn't think he clicked the button (at all), but is not 100% sure... however S3 icon issue persists | 2015-12-09 | James - 45Press | ON HOLD | ON HOLD | 12/15/15 - John identified bug w/ Gitlab - Object Stores fail without clear error- Desman does not get notified of the error from GitLab... Bug filed in issue tracker (#131) being investigated 12/23/15 - attempting to reproduce the problem (may be related to 0-byte files?); still investigating 01/06/16 - has not occurred again in production
37 | SONYDFA-512099 | Error accepting production merge; Stuck in maintenance mode | Accepting Merge Request | mackwilds.com 500 Getting a 500 error after accepting merge for production. -The issue looked to be that the service was stuck in maintenance mode which prevents any jobs to queue and not execute. Once that was removed, we were able to restart the prod creation routine. | 2015-12-11 | Ray - 45Press | ON HOLD | ON HOLD | 12/15/15 - John F thinks it could be DB related; John to touch base with Mike L. 12/23/15 - to be investigated 01/06/16 - need to reproduce this with user next time it happens; need steps to reproduce
39 | SONYDFA-512680 | Devel & Stage Buttons appear without actually promoting to stage | Site Creation | robertjohnsonbluesfoundation.org Ray: Something a bit odd with this site. After I created the site in desman, I noticed that the stage button appeared along side the devel button, without me actually promoting anything to stage. Devel created with no problem, but after doing the real promotion to stage it appears to have failed. Would you be able to force this into stage so I can get it into scan? | 2015-12-14 | Ray - 45Press | ON HOLD | Unable to Reproduce | 12/15/15 - Unclear what happened in this instance...need to reproduce the problem; see if it happens again
48 | SONY-517002 | Archer Website ID, creating DEV environment | Preview URL | bmthofficial.com JF - Ok well I will look into this further to see if I can determine why there was a second request for the assessment, but thank you for confirming that it's ready to go. If I can determine a cause for the second assessment request I will file a bug so we can work to prevent this from happening. Unfortunately so far I've never seen this happen in the lab or been able to reliably reproduce the issue. | 2016-01-06 | Neato | ON HOLD | INetU Investigating | 01/06/16 - looks like user tried to review merge request very shortly after creating, but Neato saying not the case. A 2nd deployments fired off to create assessment, one failed... When user accesses merge request page...triggers a different event type--MAY be triggering a new assessment, but unclear -same issue as #1 from 11/13/15 -Implementation of 2.1.4 could reduce the frequency of this happening because when a pending security assessment is issued, because we will be attempting to hide the "Review Pending Merge Request" button. However, if Desman's process completes before the Archer API message back to Desman, then the button may still appear (until user logs out and back in/or refreshes page)... so need to see if this change reduces the frequency of this problem 1/14/16 - JF unable to reproduce in lab; adding additional logs to try to capture this issue as it happens in production 1/20/16 - Putting this on hold until logs can capture an instance of this happening in production
Note on H1: OPEN -reported and clarification and specification not finalized READY FOR DEV READY TO TEST ON HOLD -it is not worked on CLOSED -successfully tested REMOVED -not applicable/nothing will be done for it

## CLOSED
Issue # | Priority | Reference # | Subject | Area | Description | Date | User | Status | Resolution | Notes
1 |  | SONYDFA-504051 | Security Assessment Pending - Error Multiple assessments being created | Production - Security Assessments | JF - There was an error that had occurred while the assessment was pending. This could be due to a second assessment being requested after another recent merge. I acknowledged the error inside the deployment history. After the assessment complete you may accept the latest merge into prod. After it completes you may merge new changes without requesting an assessment. Until it completes it will cause warnings and make you submit new requests each time you try to merge changes into prod. | 2015-11-03 | RCA | CLOSED | Timing Issue - User Communication | 11/19/15 - leave merge request alone (do not accept stage/prod requests) until security assessment is completed... otherwise will result in a double-assessment Pending Assessment notification exists in Desman, but users can still trigger/accept merge requsts (stage->prod) via GitLab Users should see a green badge on the main site screen that tells them the assessment is complete. In the meantime they cannot accept any merge requests outside of Desman via GitLab Currently unable to prevent users from accepting merge requests via GitLab; in future, need to determine if there's a way to control this 11/24/15 - To explain this issue to users during Desman 2.1 call on 11/25 12/1/15 - video tutorials to be created by Chris/John to help illustrate this point in the Devel->Stage push 12/8/15 - Tip sent to users on this today 12/9/15 - Ray/James -Giving a few minutes between tasks helps them to avoid problems. However, can we add functinoality to hide the Review Latest Merge Request button until the assessment has a completed status? (i.e. not only when the assessment is being created) Also: Why does "Review Latest Merge Request" button launch a new security assessment? The intent when clicking this button is only to 'review', not to accept the request 12/15/15- Again, triggering merge requests too quickly in succession will cause problems...
3 |  | N/A | S3 Promotions Issue | Production - S3 Object Store | John addressing S3 Promotion issue (mentioned in Friday status mtg) | 2015-11-12 | John Fanjoy | CLOSED | Desman 2.1 | 11/19/15 - currently no S3 Object Store automation, but will be available with 2.1
4 |  | SONYDFA-506184 | Automatic Object Storage Promotion | Production - Promoting To Stage | Attempting to promote parsonjamesofficial.com content to stage but it did not work; This was due to object storage portion of deployment; Object store promotion functionality needs to be enhanced so that it is automatic when the user promotes site | 2015-11-12 | Ray - 45Press | CLOSED | Desman 2.1 | 11/19/15 - currently no S3 Object Store automation, but will be available with 2.1
6 |  | N/A | Desman 2.1 Demo - Container Creation did not resolve | Desman 2.1 - Container Creation | During Desmon 2.1 demo, progress indicator icon for creation of a container (when building Stage environment) kept running/did not resolve... could be related to an issue with export of S3 bucket contents from Devel to Stage (John looking into it) | 2015-11-10 | John Fanjoy | OPEN | Desman 2.1 | Fixed in Desman 2.1 release
7 |  | N/A | Desman 2.1 Demo - Cron Job error | Desman 2.1 - Cron Job Module | Cron Job creation had an issue when creating new job (John looking into it) | 2015-11-10 | John Fanjoy | CLOSED | Desman 2.1 | Fixed in Desman 2.1 release
9 |  | SONYDFA-506807 | Security Assessment requested when changes promoted from stage to prod | Production - Security Assessment | sonymusic.co.kr: Unfortunately it looks like an assessment was requested when the changes were promoted from stage to prod. If the site is already live in Prod then when you promote changes from stage to prod you can click the "No Assessment Required" (Red) button. That will automatically promote your changes without submitting an assessment. You can ask InfoSec to cancel or pass the assessment and it should rebuild with the new changes depending on if it passed. If they cancel it then you can re-promote using the button with selecting the "No Assessment Required" button. | 2015-11-16 | Ray - 45Press | CLOSED | User Error | 11/19/15 - Not sure we really have a bug here...need to discuss with Ray to determine...site was in remediation when he attempted to go to Prod...may be OK Ray - 11/24/15 -original ticket was created because the site was live in Prod, but it was still showing being in remediation... i.e. almost as though one hook/trigger didn't fire correctly and it was stuck. Because it was in a status of remediation, not able to promote additional changes to production; only have seen this one time so far Brian - 11/24/15 - looks like user may have accidentally triggered a 2nd assessment (when prompted, user should choose not to launch a new assessment); we can keep an eye out for the same issue...could be a training issue... Although since new scan went into remediation.. Brian confirmed there was a Admin/admin id/password for Wordpress issue... Ray fixed it, and then they pushed it through
10 |  | SONYDFA-507314 | Site down in stage | Production - Stage Env | Getting a 500 error on the stage district: http://213-stage.paas-s.smehost.net/ which is holding up scan. Can someone look into? | 2015-11-16 | James - 45Press | CLOSED | Bug Fixed | 11/19/15 - Load balancing proxy conflict bug... Staging site going to non-existent port...this was a development deficiency that was addressed so this should not occurr going forward. This bug was fixed via a micro-release so it should not happen going forward.
11 |  | SONYDFA-506851 RFE# 126 | Deploy to Devel Failed | Production- Deploying to Devel | chrisbrownworld.com: Got "One or more deployments has failed. - /websites/Please contact an administrator to continue" when pushing some theme changes to devel. Later Issues: Can we get the prod URL checked here (its blank), also OBS promoted to prod? > http://225-prod.paas-p.smehost.net/ | 2015-11-17 | Ray - 45Press | CLOSED | Released 2.1.4 | 11/19/15 - This ends up in an error log that is created as the deployment is happening...notifies user that there is a problem; Log: Error occurred while trying to save the Archer assessment...the actual site environment deployed completely (and successfully) but this part of it issued the error; it was re-run and saved Archer assessment correctly 11/24/15 - Brian/John began looking into it... found that an error needs to be acknowledged due to 2nd request... still looking into it... also see #1 12/1/15 - Theory: If a user tries to review a merge request too quickly after having launched a security assessment (after having created merge request), then the 2nd request will not see that an assessment request has been kicked off... potential for two request events to be triggered too closely together... can we create a delay for the merge request review button to appear? i.e. do not show the merge request button until after we have successful "Pending" assessment request - John to create RFE to create this as mitigation tactic: 12/2/15 - Merge request button should be hidden from view until after assessment request creation #126 12/8/15 - Tip sent to users on this today 12/8/15 - RFE To be addressed after a handful of existing bug fixes are done (i.e. tied to Archer URL issue, etc) 12/9/15 – Ray/James – This feature will be helpful, but why does "Review Latest Merge Request" button launch a new security assessment? The intent when clicking this button is only to 'review', not to accept the request 12/15/15 - RFE in progress 12/23/15 - Targeting first week in Jan for release 01/14/16 - To be released today
12 |  | SONYDFA-507314 | Container Port issue | Production - Container Port Issue | fantasiaofficial.com: The site is now available through the stage URL. http://213-stage.paas-s.smehost.net/ This issue was already addressed. A site that was created as a result of a push a couple weeks ago had the same port which was causing haproxy to not forward the request to the correct server. I removed the container with that wrong port which fixed this issue. | 2015-11-17 | James - 45Press | CLOSED | Duplicate | This is a duplicate - SEE #10
13 |  | SONYDFA-507347 | Image Object Store Issues | Production - S3 Object Store | mackwilds.com: Not that I am aware of. Here's the same site on our dev environment where it is working: http://projects.45press.com/mack-wilds/ Maybe the rev slider plugin is having issues with object store? Either way those URLs should be in the database, possibly escaped or encoded and thats why? | 2015-11-17 | James - 45Press | CLOSED | Desman 2.1 | 11/19/15 - currently no S3 Object Store automation, but will be available with 2.1
14 |  | SONYDFA-500807 | Deploy to Devel Failed | Production - Deploying to Devel | johnlegend.com INetU- You'll have to make a few changes before you push. Devel, Prod, and Stage were set up. Something caused these to not be created. There was nothing to merge going to stage. Please make some changes then try to do the deploy. Ray - Theme and plugins are committed, but it looks like that didn't automatically deploy to dev with desman? | 2015-10-20 | Ray - 45Press | CLOSED | Communicate to Users | 11/19/15 - Originally, Git Repo was not moved to the label group; INetU made manual steps to correct, but this could have led to other issues... Need to go back and do more analysis on the root issue 11/24/15 - Pending INetU review 12/1/15 - naming conflict because Git Repo was pre-existing; created outside of Desman...so when it was re-created within Desman... Desman could not integrate it correctly; migration issue... need INetU to migrate Git Repo in these cases.... need to communicate to Ray/James that they must let INetU migrate stuff from outside of Desman into Desman 12/8/15 - Tip sent to users on this today 12/9/15 - Ray/James - will keep lookout for these issues
15 |  | N/A | Google Authentication Login problem or page content issue? | Production - Wordpress Login/Google Authenticator or page content issue? | sonymusic.co.kr Tae-Hueng Kim (Korea) -Once he logs into wordpress, he can get his key and code from his account page. I am unable to setup that portion of it for him, but basically the phone app, once setup, will provide one time use codes to login to the site with ...The plugin is disabled but he can’t login because of invalid password. Please check if his ID or password is correct. If not, please reset his password. ...> Now his admin login with Google Authenticator works fine. Another problem. After he uploads new contents, we open the site and we found there is something wrong in the page. Please see the screenshot in red box. | 2015-11-17 | James - 45Press | CLOSED | Word Press Issue | Not applicable - WP issue (not Desman)
16 |  | SONYDFA-506851 | Blank production link | Production - Blank production links | chrisbrownworld.com Can we get the prod URL checked here (its blank), also OBS promoted to prod? > http://225-prod.paas-p.smehost.net/ | 2015-11-17 | James - 45Press | CLOSED | Duplicate | 11/19/15 - Not sure how it was manually resolved... need to investigate further to identify root; Note that #11 is a different issue that happened with the same site 11/24/15 - Brian/John began looking into it...related to accepting merge request before assessment completed; containers get created, but code does not get pushed
17 |  | SONYDFA-507855 | Devel environment creation performance | Production - Devel environment creation | iggyandthestoogesmusic.com Stuck on creation; Looks like it finally went through, took about about 20 minutes though, usually it creates within a few minutes. | 2015-11-18 | Ray - 45Press | CLOSED | Desman 2.1 | 11/19/15 - Could be that there were more jobs in the queue; new Desman will have the user-feedback to allow user to see that it's taking longer; if necessary, can create an enhancement that logs how long it takes to deploy, collects telemetry of start/end times, allows you to create reports, and predict average response time (to create RFE)
19 |  | SONYDFA-507607 | Deploy to Devel Failed | Production - Deploying to Devel | outkast.com It appears my initial commit did not automatically deploy to devel: http://228-devel.paas-d.smehost.net/ | 2015-11-17 | Ray - 45Press | CLOSED | User Error | 11/19/15 - Ray confirmed issue on his end - Not Desman
23 |  | SONYDFA-507634 | Promote Object Store to Prod | Production- Object Store | leonardcohen.com Need OBS promoted to prod | 2015-11-20 | Lori Scanlan | CLOSED | Desman 2.1
24 |  | SONYDFA-508312 | Promote Object Store to Prod | Production- Object Store | thestrokes.com Need OBS promoted to prod | 2015-11-20 | Lori Scanlan | CLOSED | Desman 2.1
25 |  | SONYDFA-508072 | Promote Object Store to Prod | Production- Object Store | iggyandthestoogesmusic.com Need OBS promoted to prod | 2015-11-20 | Lori Scanlan | CLOSED | Desman 2.1
26 |  | #SONYDFA-509018 | Create Site failed | Production - Create Site | official-grace.com Attempted to create this site in Desman and got "One or more deployments has failed." | 2015-11-24 | Ray - 45Press | CLOSED | Micro Release 2.1.2 Fixed | 11/24/15 - Pending INetU review 12/1/15 - Git Repo was deleted & re-created; someone pushed an empty Repo which deleted it... Looks like user error. Theory: user tried to Clone Git Repo from Desman/GitLab while it was still generating repo? As a result, they got a blank repo, and uploaded it, wiping it out after it was actually created; still needs analysis. 12/2/15 - Related to the site official-grace.com, and upon investigation it was discovered this was actually related to the git push bug we identified in version 2.1.1 of DeSman which was resolved in v2.1.2 on Wednesday of last week.
28 |  | #SONYDFA-505887 SONYDFA-510333 | GitLab/Desman problem | Git - pushing changes | rca-records.co.uk Everything completed fine. We are looking into why when you push it doesn't show as completed and end maintenance mode. I have manually marked everything as completed and ended the maintenance mode with the drop down button. | 2015-11-27 | Alice | CLOSED | Micro Release 2.1.2 Fixed | 12/1/15 - Git Push icon... stuck in a running state even though process had completed; it may have been that Alice tried to do some processes manually outside of Desman (when she should have done them via Desman)...i.e. she moved the project herself from her personal namespace to another group she created (All Color Bright - ACB) via Gitlab--because it wasn't moved via Desman... could a user creation error have kicked off this chain of events? 12/2/15 - was related to rca-records.co.uk and the result of user error both on the part of INetU and the developers from the ACB group. The ticket (SONYDFA-505887) was actually not directly related to the DeSMan issues so we have created a new ticket where we will track the progress on resolving the issues with this site in Gitlab and DeSman. This ticket is SONYDFA-510333 which is being handled by Mike Lilly, but I will be helping him once we have the necessary information to move ahead with it. 12/8/15- fixed in 2.1.2 12/9/15 - No issues since went live
29 |  | #SONYDFA-508072 | Security Assessment? "stuck on pending" | Production - Security Assessments | iggyandthestoogesmusic.com The git push actually finished. For some reason it is just not reporting that it is completed and stuck on pending. Also I have promoted OBS content and fixed the image URL's as they weren't displaying. | 2015-11-25 | Legacy | CLOSED | Micro Release 2.1.2 Fixed | 12/1/15 - push event completed, but error in how git was handled on working copy... Impacted status of deployment; John created/released micro-release to fix which updated Git software 12/9/15 - No issues since went live
30 |  | #SONYDFA-509222 | Did not display completed (?) | Icon status indicators | chrisbrownworld.com In reference to the other tickets, the push completed however it did not display that it was completed. I have pushed the changes to prod as well. | 2015-11-25 | Ray - 45Press | CLOSED | Micro Release 2.1.2 Fixed | 12/1/15 - push event completed, but error in how git was handled on working copy... Impacted status of deployment; John created/released micro-release to fix which updated Git software 12/9/15 - No issues since went live
31 |  | #SONYDFA-509207 | Icon indicated Git still running, but actually completed | Icon status indicators | leonardcohen.com Icon stuck in git push, but Ray determined that it had in fact already completed... | 2015-11-25 | Ray - 45Press | CLOSED | Micro Release 2.1.2 Fixed | 12/1/15 - push event completed, but error in how git was handled on working copy... Impacted status of deployment; John created/released micro-release to fix which updated Git software 12/9/15 - No issues since went live
33 |  | #SONYDFA-510415 | Deployment timing issue | Git - pushing changes | thebuffet.r-kelly.com It looks like you probably pushed your changes into git before everything was in place. For example, if you push your changes before the hooks are configured in gitlab, then a message won't be sent to desman to trigger a deployment. This should only be a possible issue for a short time after a site is set up. If you run into this again, a new commit will trigger a deployment. In this case, I added a standard entry to .gitignore and pushed it to devel. That triggered a deployment and now your code is running in devel. | 2015-12-03 | Ray - 45Press | CLOSED | Timing Issue - User Communication | 12/8/15 - Pushed changes to Git Repo before it was set up; web hooks not added yet... Button not displayed, but since users knew path to repo outside of Desman they were able to push the changes; happened at beginning of site creation...they need to slow down. - Bill to create new Tip related to this particular instance 12/9/15 - When Ray gives it an extra min or two between tasks this improved things; we should keep lookout for problems even after Git Repo icon resolves in Deployment status section
35 |  | #SONYDFA-510415 | Deployment to Devel |  | thebuffet.r-kelly.com It looks like a race condition prevented the promotion from completing, but that has been cleared and the site is ready in stage: http://237-stage.paas-s.smehost.net/ -David Six | 2015-12-03 | Lori on behalf of James 45Press | CLOSED | Timing Issue - User Communication | 12/8/15 - multiple deployments triggered simultaneously... or very closely together; i.e. if you push to all 3 branches simultaneously, it'll cause problems... Users need to push to Devel first, then promote to other branches -Users need to wait to push changes to 3 separate branches; wait may only need to be a few seconds -Bill to add to list of Tips 12/9/15 - Ray/James: is there a way to create a block so you can't update Stage to Prod if Dev to Stage has not completed?; Ray has been giving things more time between pushes and things have been better, but when other users come onto the system it will be a learning curve for them 12/15/15 - Git does locking that will prevent multiple pushes; more a problem with regional admin users (with elevated ability to push to environments) - Deployment status indicator should be indicator of when you can procede with push to stage, etc -Bill to add to training doc
38 |  | SONYDFA-512099 | Stuck in maintenance mode |  | mackwilds.com 500 -The issue looked to be that the service was stuck in maintenance mode which prevents any jobs to queue and not execute. Once that was removed, we were able to restart the prod creation routine. | 2015-12-11 | James - 45Press | CLOSED | Duplicate | 12/15/15 - Likely to be related to above issue 12/23/15 - to be investigated
40 |  | RFE #135 | Default Deployment Status area to be expanded (instead of closed) | Deployment Status | Currently the Deployment Status area defaults as closed... If we default it to expanded, users will see the progress indicators right away (i.e. they may not know to open that area to view progress) | 2015-12-15 | John F | CLOSED | Released in 2.1.3 | 12/15/15 - to create RFE for this enhancement 12/23/15 - to be included in 2.1.3 RFE #135
44 |  |  | When security scan pending, warn user if they click orange merge request button... | Security Scan Pending | If users click the orange Review Latest Merge Request button... Can we have system give user pop-up error saying "WARNING: Accepting your merge request before the security assessment is completed, will cause system problems. Please wait to accept your merge request until you see a green "Completed" notification for your security scan." | 2015-12-17 | Bill | CLOSED | duplicate | 12/23/15 - same as 126- we're not even going to show the button
45 |  | SONYDFA-514158 | Stage to Prod deployment stuck | Stage to Prod Deployment | robertjohnsonbluesfoundation.org this site appears to be stuck going from stage->prod. It's been nearly 40 minutes and the container build is still listed as in progress. can you please check? | 2015-12-21 | James - 45Press | CLOSED | Networking Issue | 12/23/15 - Issue related to Jenkins - container builder - network configuration change made and should be permanently resolved
46 |  | SONYDFA-513668 | OBS viewing error/insecure response issue | OBS | kidinkmusic.com I had Brian load the site up and it did not load for him even though it continued to load for me after clearing the cache! Turns out that method of viewing OBS only works for the first person to request it when accessing it over https, hence when I cleared the cache and was the first to view it, it did not show an error for me. | 2015-12-21 | James - 45Press | CLOSED | Not Desman issue | 12/23/15 - Need to confer with Mike to investigate; may not be tied to Desman... Gen 2... But using OBS so could be tied to Desman workflow 01/6/16 - Issue tied to constructing URL for OBS resources; if use bucket name in domain name and not in path could cause issues... not Desman related; we should instruct users to use the path method going forward
47 |  | SONYDFA-505887 | Archer Website ID, creating DEV environment | Preview URL | rca-records.co.uk We’re trying to make a couple more changes to the site before it goes live. Unfortunately, an error occurred when I tried to promote the database content from Stage to Prod. I since managed to do a manual export and import via the SFTP interface, but the “Current Deployments” section in DeSMan is still showing red and blocking me from doing much. Could you please: 1. Drop the Prod MySQL database and do a fresh import of the database from Stage 2. Release the DeSMan interface for me so I can carry on working on the site | 2016-01-04 | Alice Rose - A Color Bright | CLOSED | User Error | 01/06/16 - User exported DB and then changed name of it... tried to promote it after renamed... DB does not auto-update based on name changes... User should avoid renaming DB files during export/import, etc.
49 |  | SONY-517945 | Docker Sandbox on InetU | Preview URL | InetU, Regarding the issues we had with the deployment process and our composer file I would like to ask if it would be possible to get something like a sandbox from you guys, in which we could simulate the entire deployment process. Just one host with the same setup as the PaaS has but without stage and prod. We just need to figure out a flawless deployment setup. In addition a SSH login to that sandbox would be really great for testing purposes and to restart these processes which we have ask you guys usually. Why I'm asking for this is the fact, that we always have to wait for you guys (no offense, just the time difference) to make specific things like restarting a docker deployment if something had failed or the deployment got stuck. Also to lean how the system really works. If you have any questions don't hesitate to ask. Kind regards Anton | 2016-01-11 | Anton - Germany | CLOSED |  | 1/14/16 - The sandbox is really the current "Devel" environment; guiding Anton on how to reproduce the Docker container locally
8 |  | N/A | Desman 2.1 Demo - Show Current Deployments buttons automatically | Desman 2.1 - Deployment Status Indicators function | When all of the processes are completed for a given deployment (i.e. all icons change to ones with green checks), can we have the environment button (i.e. the green “Devel”, “Stage” or “Prod” buttons) automatically appear (instead of the user having to manually refresh the page) | 2015-11-10 | Tony Shin | CLOSED
42 |  | SONY-513299 RFE #136 | Uploading 200MB file via OBS file browser not working | OBS File Browser | We are trying to upload a 200MB file via the OBS file browser in DeSMan. This just don't works. We don't get any error message. The upload runs until 70%, starts from scratch and then just aborts. | 2015-12-15 | Anton - Germany | CLOSED | Released in Desman 2.2 | 12/17/15 - RFE created for the bug; David S: I have tested and confirmed what you found with the Object Storage Browser in Desman - I am able to upload a file up to 100MB, but not 150MB or larger. I have opened a bug for this 12/23/15 - to be worked on - no timeline for now 01/6/16 - Not in this weeks micro release; shooting for next one (i.e. need multi-part upload capability for larger files) 01/14/16 - To be released with all OBS enhancements... 1-2 weeks... update next week
53 |  |  | Stage URL Not Passing to Archer Consistently | Archer interface | For the following sites, the stage URL was not passed to Archer during the security assessment request: celinedion.com antoniolizana.net | 2016-01-22 | Bill | CLOSED |  | 1/27/16 - Related to the high volume of work (above issues); NOTE: Stage URL is sent during the push to Stage--check: Confirmed functionality working now…recently promoted to stage site, https://www.fourmusic.com/, APP-239452, shows preview URL
54 |  | #SONY-521037]: Desman - Halo - marenmorris.com - Stage button not appearing #SONY-520602]: Halo / marenmorris.com - file promotion | Deployment to Stage - button not showing | Deploy to Stage | marenmorris.com Users deployed to Stage and all processes look to be completed, but Stage button does not appear so they are stuck | 2016-01-25 | Jamie - Nashville | CLOSED |  | 1/27/16 - Completed status needed to be manually triggered; could be related to Wordpress version mass update…create many deployments at the same time
55 |  |  | Duplicate security assessments issued? | Security Assessments | pinkspage.com Lori indicated that multiple ASM numbers/records were created for this site in Archer…trying to determine what happened Si - Infosec: I already scanned the APP-115408 with ASM-4219. Is ASM-4223 a duplicate? | 2016-01-26 | Lori/45Press | CLOSED | To delete extra security scan from Archer and Desman | ASM-4219 - First Published: 1/22/2016 3:38 PM Last Updated: 1/25/2016 1:21 PM ASM-4223 - First Published: 1/25/2016 4:13 PM Last Updated: 1/25/2016 4:13 PM While there was the first assessment pending, user probably tried to create a new merge request to production and triggered a new assessment -system will have prompted them that an assessment already exists, do you want to create another? They could have said YES We need to delete 4223 in both Archer, and in Desman...so that the correct, completed one, 4219 shows in Desman
51 |  | #SONY-519721]: uk/ desman - raleighritchie.com | Archer Website ID, creating DEV environment | Preview URL | raleighrichie.com Within Desman, I've clicked the 'promote changes' button to update files from Devel to Stage for www.raleighritchie.com, then I've accepted the merge request in GitLab. However, the git push seems to still have the status "in progress" and I'm not seeing the updated site on the stage link (http://151-stage.paas-s.smehost.net/). I've looked at the file list for Stage in GitLab, and the theme files look like they've moved across, but I'm seeing no evidence of that in the on the Stage link. | 2016-01-19 | Terrance Summerbell - UK | CLOSED | User Training | 1/19/16 - Brian B: The error is showing "prepared_devel_17-03-15_1426616377.sql not found" This happens when you click promotes changes and the last exported file name has been removed or renamed. If you export a database file and change the name you should use the "Import from File" option. Use "Promote Content" after you export a database and don't plan on changing the file. ->Training 1/20/16 - Bill to create new Desman 'Tip' for user consumption 2/10/16 - Will keep a lookout for users falling into this issue... but has not happened again
56 |  |  | WordPress 4.4.1 Mass Update | Wordpress Update | The mass WordPress 4.4.1 update process ran and an error in the script created ~150 additional jobs causing Desman performance issues, but also created residual problems on the platform that need to be resolved; system was offline on Tuesday, and put back online in a working, but not optimized state; INetU working to restore it to optimized state | 2016-01-26 | Multiple | CLOSED |  | 2/2/16 - Would more hardware capacity have helped lesson the severity of this issue? 2/10/16 - David made changes to script to improve it
68 |  |  | WordPress Login Problem - CloudFlare Page |  | It happens when cloudflare does its DDOS check if it's the first time you are attempting to login after awhile. Just happened on http://www.jefflynneselo.com/ [10:29:32 AM] James Fortunato: Sometimes when you go to login, you get a cloudflare page, and it then says your password is wrong, but it's not [10:29:34 AM] James Fortunato: so you have to try again [10:29:38 AM] James Fortunato: and then it works [10:29:48 AM] James Fortunato: it's confusing some of the labels | 2016-02-04 | James - 45Press | CLOSED | CloudFlare Issue - Not Desman | 2/10/16 - WAF (web app firewall) security issue? Need screenshot from James… maybe there's a way we can address it or at least inform the users; will follow up with issue offline
43 | A | RFE #138 | 502 Error upon Website creation - after 1st git push - Load Balancer Issue | Create Site | 502 Error first time previewing site after first git push (i.e. from video demo) due to lingering load balancer changes (i.e. when going into Plugins in WP admin during load balancer changes) | 2015-12-16 | Bill | COMPLETED | Went live 2/17/16 | 12/23/15 - Short term: create a more friendly 502 error... (RFE #138 Users presented with 502 during container deploy) 01/06/16 - implemented the friendly 502 error... This will be a training issue until --current Marathon configuration does not use Zookeeper... but to do this would be overhauling the system... could take a while... need to prioritize it for later 1/14/16 - Putting larger overhaul on hold for now (begin end of Feb -in 6 to 8 weeks) currently a user training issue (i.e. they must refresh the page after a few seconds) 2/10/16 - Temporary fix in place (i.e. 1 min reloads)... but ready to begin work on implementing Zookeeper 2/17/16 - Back to event-driven version of Marathon; already live
41 | A | RFE #139 | Make Deployment Status environments a static order | Deployment Status | Currently, the different environments shift order (Devel, Stage, Prod, etc) in relation to user activity... It may be clearer if these rows were static | 2015-12-15 | John F, Chris G | CLOSED | For Version 2.3 | 12/15/15 - RFE exists for this enhancement 12/23/15 - targeting next release (1st week January) RFE #139 01/06/16 - Not in this weeks micro release; shooting for next one 01/14/16 - Will try to slip this into release (smaller issue)--borders on cosmetic issue 01/20/16 - In progress 02/10/16 - Rajeev completed, to be reviewed/merged for future release
64 | A | RFE-147 | Display Preview URLs on main site page - making red button clickable | Main Site Page | Display the full preview URLs for Devel, Stage & Production under the existing Devel, Stage & Production buttons. Currently, you have to click to view one of these environments to see the appropriate URL, however, if the buttons are in an orange or red state, you cannot access them. It would be good to still be able to see these pages even if the site is in a locked state. | 2016-01-28 | Neato - UK | CLOSED | For Version 2.3 | 1/29/16 - JF, DS - We can keep the button clickable even though it's in a red state 2/10/16 - very simple to change… can add to next release
65 | A | RFE-143 #SONY 481311 | Allow ability to deploy static content along side WordPress |  | Putting files in the root of a WP site and getting deployed properly; Creating a separate directory structure for static version of the site in Git repository, alongside WordPress | 2016-01-29 | Conference | CLOSED | Separate Release (Friday 2/19) | 2/3/16 - High on Columbia's priority list 2/10/16 - can be done relatively quickly; John to get ETA so we can set Columbia's expectations 2/17/16 - separate from version 2.3 itself (part of WordPress repo) - shooting for working functionality for this Friday
69 | A | RFE-146 | Merge Request Button not appearing after push, promote to stage |  | James did a small update (replaced image file) and pushed changes to Devel; we waited until the Git push and container processes resolved, then chose to Promote Changes (to Stage). At this point the "Accept Latest Merge Request" button did not appear... James went into GitLab separately to accept the merge request The button did not appear again when choosing to promote changes from Stage to Prod | 2016-02-09 | James - 45Press | CLOSED | For Version 2.3 | 2/10/16 - John to investigate this (could be bug introduced from previous work to hide button)… as a workaround users can scroll all the way down to the Git section of the page to access the merge request there 2/17/16 - merged into 2.3
69 | A | RFE - 150 | Stage URL not sent to Archer |  | Christina Aguilera APP-119402 ASM-4259 http://280-stage.paas-s.smehost.net/ | 2016-02-16 | James - 45Press | CLOSED | Released in 2.4 | 2/17/16 - could be a PHP availability issue going on; John to look into this 3/2/16 - John has a fix planned to implement but sidetracked by production support; this issue effects other processes such as processes being marked complete - as more users get on the system, this issue will grow so this fix will allow app to scale up 3/8/16 - More sites with Stage URL issue: vergeredcords.com.au (3/8/16) App Push-Notification Service (3/8/16) Essential Artist Services (Provident) (2/17/16) valentine.rachelplatten.com (2/10/16) 3/9/16 - John began work and nearly done w/ microservice to support PHP services ---shooting for Tuesday 3/15 3/16/16 - Working out kinks with Jenkins jobs--occasionally not marked as complete and fill up the queue
70 | A | RFE- 151 | Restarting a database create job fails (but looks like success) | Database Create | Restarting a database create job fails (but looks like success) - (db create happens but not marked as complete and if you hit restart, it messes things up) | 2016-03-02 | John F | CLOSED | Released in 2.4 | 3/2/16- John working on a fix for this for next micro release 3/16/16 - PHP issue resolution will reduce risk of this problem… would be a smaller issue, but still needs to be addressed
71 | A | #SONYDFA-533305 | #SONYDFA-533305: au/ sonymusic.com.au - Merge request to Stage |  | The Staging site is now available however the latest database and Object Storage were not promoted and all the images were missing along with some content. I managed to manually promote the DB and OBS storage and everything is up to date now. | 2016-03-23 | Andrew Meli - Red Unicorn - AU | CLOSED |  | 3/24/16 - The DB & Object Store is only deployed from Devel to stage on the first push to Stage… and this is on purpose; this is to prevent updates to production from overwriting any DB/Object Store changes that occurred in production. - Bill to clarify with user and send a tip out to all users.
Note on I1: OPEN -reported and clarification and specification not finalized READY FOR DEV READY TO TEST ON HOLD -it is not worked on CLOSED -successfully tested REMOVED -not applicable/nothing will be done for it

## Screenshots
53
55
69